Contract for

SIS100 Power Converter

LOT 1

2 units of Power Supply for SIS100 Radiation Resistant Quadrupole Magnets

Appendix 7 Schedule

# Objective

This Annex establishes the Schedule within the meaning of Section 3 of the Agreement as well as the milestones.

# Schedule

| No. | Designation | Date | Type |
| --- | --- | --- | --- |
| 1 | Award of contract |  | M, P |
| 2 | Conceptual Design Review (CDR) | 2 months after No. 1 | M |
| 3 | Final Design Review (FDR) | 2 months after No. 2 | M, P |
| 4 | Provisions | 2 months after No. 3 | M |
| 5 | Factory Acceptance Tests (FAT) | 6 months after No. 3 | M, P |
| 6 | Shipment |  | M |
| 7 | Site Acceptance Tests (SAT) | 1 month after No. 5 | M, P |
| 8 | Delivery and Acceptance of Documentation | 1 months after No. 7 | M, P |

Types of deadlines: M = milestone, P = payment, T = time limit.