Vertrag über die Herstellung, Lieferung und Tests von Coils für 18GHz ECRIS

Anlage 10 Terminplan

# Zielsetzung

Diese Anlage legt den Terminplan iSd Ziffer 3 des Vertrages sowie die Meilensteine fest.

# Terminplan

| Nr. | Bezeichnung | Datum | Typ |
| --- | --- | --- | --- |
| 1 | Award of contract | T0 + | M, Z |
| 2 | Conceptual design Review und (CDR) and Final Design Review (FDR) | + 4 Monate | M, Z |
| 3 | Coils assembled | + 10 Monate | M |
| 4 | Coils Factory Acceptance Test (Siehe Section 5.1.1-5.1.5 of the “Coils Detailed Specification”) | + 11 Monate | M |
| 5 | Complete system Factory Acceptance Test (Siehe Sections 5.1.6 and 5.1.7 of the “Coils Detailed Specification”) - 3D Mapping (longitudinal axis included) of the magnetic system for three different combinations of current levels provided to solenoid1, solenoid2 and solenoid3, respectively: 1100A-660A-1100A, 90%-90%-90%, 80%-80%-80% - Thermography for three different combinations of current levels provided to solenoid1, solenoid2 and solenoid3, respectively: 1100A-660A-1100A, 90%-90%-90%, 80%-80%-80% | + 12 Monate | M |
| 6 | Solenoids Transport | + 13 Monate | Z |
| 7 | Site Acceptance Test (SAT) (Siehe Section 5.2 of the “Coils Detailed Specification”) - 3D Mapping (longitudinal axis included) of the magnetic system for three different combinations of current levels provided to solenoid1, solenoid2 and solenoid3, respectively: 1100A-660A-1100A, 90%-90%-90%, 80%-80%-80% - Thermography for three different combinations of current levels provided to solenoid1, solenoid2 and solenoid3, respectively: 1100A-660A-1100A, 90%-90%-90%, 80%-80%-80% - Coils geometrical and technical inspection | + 14 Monate | M, Z |

Art der Termine: M = Meilenstein, Z = Zahlung, F = Frist.