Contract on the Design Review, Production and Delivery of Switchable Beam Dump

Appendix 10 Schedule

# Objective

This Annex establishes the Schedule within the meaning of Section 3 of the Agreement as well as the milestones.

This Annex can also be replaced by another form of schedule.

# 2      Schedule (envisaged)

Types of deadlines: M = milestone, P = payment,

| o. | Designation | Duration | Type |
| --- | --- | --- | --- |
| 1 | Award of contract | X | M, P |
| 2 | Manufacturing Design Review (MDR) | X + 1 month | M, P |
| 3 | Factory Acceptance Tests (FAT) accepted | X + 7 months | M, |
| 4 | Complete delivery to FAIR incl. documentation | X + 8 months | M, P |
| 5 | Site Acceptance Tests (SAT Ab) accepted, latest 3 months after delivery | X + 9 months | M, P |