Contract

on the Design, Development, Production, Delivery and Test of planar wave generators for PRIOR-II shock-wave experiments

Appendix 2 Acceptance procedure

# 1 Objective

This document outlines the steps of the contract acceptance process. Further details are provided in the specifications.

# 2 Acceptance Procedures

  - 2.1 The acceptance procedure consists of the following steps, which are described in more detail in this document.

# •    Final Design Review (FDR)

# •    Factory Acceptance Test (FAT) & Documentation

# Neither the FDR nor the FAT constitutes a partial acceptance. The completion of the project and, consequently, the acceptance of the generators must be confirmed by both contracting parties upon delivery of the complete documentation.

  - 2.2 FDR and FAT are performed with regards to the requirements listed in the specifications and remarks 4 through 7. Each contracting party may propose additional acceptance-related items.

  - 2.3 If necessary, the client will notify the contractor of any additional acceptance-related issues in a timely manner prior to the respective acceptance.

  - 2.4 The contractor must submit a timely written request for every milestone (FDR, FAT), and must coordinate any additional acceptance-related issues with the client in advance.

  - 2.5 FDR and FAT tests are generally conducted jointly by the client and the contractor in the presence of both parties. The contractor must provide the necessary personnel and measuring equipment for the tests at no charge.

  - 2.6 The results of the FDR and FAT must be recorded in writing by the contractor in the reports specified in section 3 (or by the client, if the contractor is exceptionally not present during the acceptance procedures) and signed by both the client and the contractor. In addition to the tests performed and their results, these records shall include, among other things, details regarding the rectification of any defects, including provisions regarding the scope and deadline.

  - 2.7 Acceptance is not replaced by successful prior use, commissioning, or governmental approval.

  - 2.8 Approval statements and acceptance records are issued based on a plausibility check conducted by the client; they do not relieve the contractor of its responsibility for the accuracy of the relevant documents, the functionality of the individual components, or the entire system.

  - 2.9 Until acceptance by the client on the client’s premises, the contractor must maintain the generators in a condition suitable for the planned experiments. The contractor shall be liable for any defects that may arise in the equipment in the meantime, unless the client is responsible for such defects or damage.

# 3 Record keeping

The contractor must request each stage of acceptance (FDR and FAT). Each step may only be requested if the previous one has been successfully completed. Each stage of acceptance must be documented in writing in the respective report and signed by both contracting parties (see Section 2.6).

# 4 Final Design Review (FDR)

  - 4.1 The requirements for the FDR are listed in the specification

  - 4.2 The technical solution for interfacing the generator to the experiment geometry must be discussed and approved by the client before the FDR.

  - 4.3 A full mechanical/geometrical documentation of the final design as well as the simulation report in accordance with the provided specifications is required for the FDR.

## Production of the generators must not begin until the manufacturing drawings have been approved.

# 5 Factory Acceptance Test (FAT)

  - 5.1 The FAT shall take place at the contractor’s premises and at the contractor’s expense. As stated in the specifications, in case of insufficient testing capabilities on the contractor’s premises, the FAT can also be performed inside the PRIOR-II blast chamber, however, suitable measurement equipment as well as any necessary customization of the chamber for the measurements must be provided and performed by the contractor.

  - 5.2 The requirements necessary for the successful completion of the FAT are listed in the specifications.

  - 5.3 The FAT shall take place in the presence of persons to be designated by the client. Both contracting parties shall confirm the successful completion of the FAT in writing in the minutes referred to in Section 3.

  - 5.4 The final report of the performed simulations and the final report of the performed characterization tests is required for the successful completion of the FAT.

  - 5.5 A full mechanical and chemical documentation of the final design is required as part of the documentation in accordance with the provided specifications.

  - 5.6 A risk analysis for the final product as well as a user manual is required.