## Relevance
| Criterion | Guiding question
| Relevance | To what extent does the project respond to the needs and priorities of political partner institutions?
No. | Evaluation question | Relevant definitions | Baseline approach | Baseline assessment standards | Intent and opportunities for learning
1.1. | This question is only relevant in the event of significant political change in the respective project country. To what extent do the intended results of the project correspond to national thematic policies and strategies of the partner governments? | 1) Intended results are all results of the project that have already been realised or are planned at the time of the evaluation, based on the reconstructed theory of change of the project. 2) Relevant national thematic policies and strategies are the most recent versions of those official documents issued by the national government of the partner country in close connection to the project results. These usually comprise Nationally Determined Contributions (NDC), National Biodiversity Strategies and Action Plans (NBSAP), or National Adaptation Plans (NAPs), but can include any other thematically relevant policies and strategies. | 1) Reconstruct a theory of change for the project (see annex 3 Guidelines on ToC Reconstruction for IKI MTEs). 2) Identify the most recent documents that provide the most detailed descriptions of the priorities and needs of the partner governments. 3) Extract all statements regarding intended targets, themes and approaches from these documents. 4) Compare the intended results of the project with the targets, themes and approaches stated in the relevant policies and strategies. | The intended results correspond to national policies and strategies to an increasing extent if a) some project results can be mapped onto any specific targets or themes mentioned in these documents b) some project results can be mapped onto any specific targets or themes, including any priority targets or themes c) the majority of project results can be mapped onto specific targets or themes mentioned in the documents d) the majority of project results can be mapped onto specific targets or themes, including any priority targets and themes. For projects focussing their efforts on the national level, level c) is expected. For projects focussing their efforts on sub-national levels, level b) is expected. | Embedding projects in partner countries as much as possible is one of the success factors for sustainable projects. If projects are found not to correspond to national policies or strategies to the expected degree, reasons for this should be explored and suggestions provided on a) if short-term adjustments to the project strategy to better fit national policies or strategies would be beneficial b) which changes to the project strategy would be most beneficial c) how a better fit between national policies and strategies and intended project results could be realised in future projects.
1.2. | To what extent do the intended results of the project correspond to thematic action plans or work programmes of the political partners on the national level? | 1) Intended results are all results that have already been realised or are planned at the time of the evaluation, based on the reconstructed theory of change of the project. 2) Relevant national thematic action plans or work programmes are those in close connection to the project results, meant to support the implementation of the national policies or strategies, as identified by the relevant political partners on the national level. | 1) Reconstruct a theory of change for the project (see annex 3 Guidelines on ToC Reconstruction for IKI MTEs). 2) Identify the most recent documents that provide the most detailed descriptions of the priorities and needs of the partner governments. 3) Extract all statements regarding intended targets, working areas and actions from these documents. 4) Compare the intended results of the project with the targets, working areas and actions stated in the relevant policies and strategies. | The intended results correspond to intermediary national action plans or work programmes to an increasing extent if a) some project results can be mapped onto any specific targets, working areas and actions mentioned in these documents b) some project results can be mapped onto any specific targets, working areas and actions, including any priority targets, working areas and actions c) the majority of project results can be mapped onto specific targets, working areas and actions mentioned in the documents d) the majority of project results can be mapped onto specific targets, working areas and actions, including any priority targets, working areas and actions. For projects focussing their efforts on the national level, level c) is expected. For projects focussing their efforts on sub-national levels, level b) is expected. | Embedding projects in partner countries as much as possible is one of the success factors for sustainable projects. If projects are found not to correspond to national action plans or work programmes to the expected degree, reasons for this should be explored and suggestions provided on a) if short-term adjustments to the project strategy to better fit national action plans or work programmes would be beneficial b) which changes to the project strategy would be most beneficial c) how a better fit between national action plans or work programmes and intended project results could be realised in future projects.
1.3. | This question only needs to be answered for projects that do in fact work within specific states below the national level or in specific municipalities. To what extent do the intended results of the project correspond to action plans or work programmes of the governments of the states / municipalities in which the project is being implemented? | 1) Intended results are all results that have already been realised or are planned at the time of the evaluation, based on the reconstructed theory of change of the project. 2) Relevant action plans or work programmes are those in close connection to the project results, meant to support the implementation of local policies or strategies and issued by the governments of the states or municipalities the project is working in, as identified by the relevant political partners on the state / municipal level. | 1) Reconstruct a theory of change for the project (see annex 3 Guidelines on ToC Reconstruction for IKI MTEs). 2) Identify the most recent documents that provide the most detailed descriptions of the priorities and needs of the partner governments on the state / municipal level. 3) Extract all statements regarding intended targets, working areas and actions from these documents. 4) Compare the intended results of the project with the targets, working areas and actions stated in the relevant policies and strategies. | The intended results correspond to national action plans or work programmes on the state / municipal level to an increasing extent if a) some project results can be mapped onto any specific targets, working areas and actions mentioned in these documents b) some project results can be mapped onto any specific targets, working areas and actions, including any priority targets, working areas and actions c) the majority of project results can be mapped onto specific targets, working areas and actions mentioned in the documents d) the majority of project results can be mapped onto specific targets, working areas and actions, including any priority targets, working areas and actions. Level b) is expected for all projects. | Embedding projects in partner countries as much as possible is one of the success factors for sustainable projects. If projects are found not to correspond to local action plans or work programmes to the expected degree, reasons for this should be explored and suggestions provided on a) if short-term adjustments to the project strategy to better fit local action plans or work programmes would be beneficial b) which changes to the project strategy would be most beneficial c) how a better fit between local action plans or work programmes and intended project results could be realised in future projects.

## Planning, Steering & Coherence
| Criterion | Guiding question
| Planning, Steering & Coherence | To what extent are the planning and steering of the project suitable to achieve the project's objectives?
No. | Evaluation question | Relevant definitions | Baseline approach | Baseline assessment standards | Intent and opportunities for learning
2.1. | To what extent were political and implementing partners, including local action actors, involved in project planning? | 1) Political partners are all organisations listed in the original as well as all subsequent project proposals under "political partner institutions" (or similar heading). 2) Implementing partners are all organisations listed in the original as well as all subsequent project proposal under "implementing partners and contractors" (or similar heading). 3) Local action (formerly called local content) actors can be either local implementing partners or local contractors. They are listed in the original as well as all subsequent project proposals under "implementing partners and contractors" (or similar heading). Formal local action requirements have been adoptet with the thematic call 2022 and all calls thereafter. | 1) Consult all project proposals to identify all political and implementing partners, as well as local action actors, of the project. 2) Identify at least one knowledgeable representative of each political partner, implementing partner and local action actor and collect feedback from them. | Partners were involved in project planning to an increasing degree if a) Inform: The project provided information to the partner to assist them in understanding the problem, alternatives, opportunities and/or solutions b) Consult: The project obtained feedback from the partner on analysis, alternatives and/or decisions c) Involve: The project worked directly with the partner throughout the process to ensure that their concerns and aspirations are consistently understood and considered d) Collaborate: The project collaborated with the partner on all aspects of the project including the development of alternatives and the identification of the preferred solution e) Empower: The project placed the final decision-making in the hands of the partner. Generally speaking, level c (involve) is expected for all implementing partners in all aspects of project planning pertaining to their field of expertise. For implementing partners possessing intricate knowledge of the project context (local partners), level d (collaborate) is expected in order to adapt the project plan as much as possible to local conditions. Regarding the political partners, involvement is expected to be limited to aspects within their responsibility (level c: involve). | Collaborating closely with other relevant organisations during project planning ensures that a wide range of knowledge, including critical local knowledge, informs project plans to increase realism and the likelihood of success. If projects are found not to have collaborated with political or implementing partners during project planning to the expected degree, reasons for this should be explored and suggestions provided on a) which partners could still reasonably be consulted regarding which topics after the MTE and b) how their input could still be incorporated into the project approach going forward.
2.2. | To what extent were other large projects or programmes funded by the German Government and working on similar themes in the project countries considered during project planning and implementation? | 1) Projects or programmes are considered large if overall funding amounts to 10 million Euros or more. 2) Projects or programmes are considered to be funded by the German Government if 50% or more of the funding was provided by German federal or state Ministries. 3) Projects or programmes funded by multi-donor funds only need to be considered if Germany was providing 50% or more of the overall budget of the fund when the project or programme in question was first set up. 4) Projects and programmes are considered to be working on similar themes if they are working on the same general topic as the project being evaluated (mitigating greenhouse gas emissions, adaptation to the impacts of climate change, preserving and restoring carbon sinks, conserving biological diversity). Both other IKI projects as well as those funded by other donors should be considered. | 1) Consult the IKI website, the IKI technical management team and / or other relevant sources (e.g. other large donors) to identify all projects or programmes meeting the criteria provided in the definitions that were / are being implemented during planning or implementation of the project being evaluated. 2) Search for evidence of coordination with the identified projects or programmes within project documents 3) Complement findings from documentation by conducting interviews with project representatives (and in particular the head of project) | A project or programme was considered to an increasing degree if a) the project team was aware of the project or programme b) meetings took place with representatives of these projects or programmes c) the project incorporated opportunities to avoid duplication of efforts or realise synergies regarding these projects or programmes. Level b is expected for all large projects or programmes working on similar themes. For projects or programmes working on similar themes as well as working with similar target groups on similar solutions, level c is expected. | Coordination and cooperation between donors, programmes and projects working on similar themes in similar areas is inteded to maximise the efficient use of scarce resources, leverage synergies and avoid duplication of efforts. If projects are found not to have coordinated with relevant projects or programmes to the expected degree, reasons for this should be explored and suggestions provided on a) which projects or programmes could still reasonably be consulted regarding which topics after the MTE and b) how synergies could still be leveraged and / or duplications avoided going forward.
2.3. | To what extent are the indicators provided in the project proposal useful for the continuous assessment of project progress? |  | 1) Identify all indicators provided in the most recent project proposal. 2) Check the usefulness of each indicator according to the following criteria: a) Does it make sufficiently clear what it is that needs to be measured / gauged? b) Is it realistically and validly measurable by project staff? c) Does it capture (one of) the most relevant aspect(s) of the underlying output or outcome? 3) Check if the indicator set as a whole enables assessment of progress over time, including during the early stages of project implementation. | Indicators and the indicator set as a whole are useful for progress assessment if they fulfil all criteria mentioned. It is expected that 75% of all individual indicators fullfill criteria a) to c). In addition, it is expected that at least 30% of all indicators pertain to changes expected to take place during the first half of project duration. | The IKI Office needs to be able to continuously check project progress against the approved project plans. Projects therefore need to report to IKI on a regular basis. Project monitoring based on indicators is intended to supplement narrative reporting with a small number of data points regarding significant changes in the project context. This data needs to be as valid and objective as possible in order to be useful. Since monitoring is intended to enable a continuous assessment of project progress, it needs to cover the early stages of project implementation as well. If project monitoring is found to be insufficient, alternative indicators should be suggested by the evaluation team, considering the administrative requirements set out in chapter 3.6 of the IKI Administrative Guidelines.
2.4. | To what extent are insights from monitoring data used for project steering and allocation of resources? | 1) Monitoring data are all data collected in connection with the output and outcome indicators provided in the project proposal and potential further data collected by the project for monitoring purposes. | 1) Collect general feedback on the usefulness of monitoring data for short- and medium-term project steering from the project team as well as the IKI technical management team, subdividing the monitoring system into output and outcome monitoring. 2) Supplement the general feedback with examples of especially useful and / or useless data, including information on how the data was used and / or explanations of why it is deemed not helpful. | To categorise the general responses, a Likert scale should be used. It is expected that both the project as well as IKI technical management team assess the usefulness of the monitoring data as high to medium. The collected examples could be helpful when developing suggestions on how to improve the usefulness of the monitoring system. | Besides supplementing narrative reporting of projects to the IKI Office, monitoring is also meant to generate data useful for short- to medium-term project steering by the project team as well as IKI technical management team. If the overall monitoring system of the project is found to be of little use for this purpose, reasons for this should be explored and suggestions provided on the changes necessary for improvement.
2.5. | To what extent does the project adapt its strategy and implementation to contextual developments? | 1) Project strategy denotes the overall project approach depicted e.g. in the project's theory of change, i.e. the project's reasoning of why certain services are provided in a certain sequence to certain target groups to support the intended effects. 2) Contextual developments are any sudden and significant developments within politics, law, economy, ecology, science and society with a direct strong connection to the topics the project is working on. Changes in national environmental politics are excluded here, as they are to topic of evaluation question 1.1. | 1) Identify any significant changes within the project context, especially within the immediate environment of the project (civil society, political and implementing partners, intended target groups) via research and inteviews with local experts. 2) Assess if any of the identified changes did have a tangible positive or negative effect on the likelihood of success of the project strategy. 3) Assess if the project changed its strategy and / or implementation accordingly, via analysis of project documents and / or feedback from project and IKI staff. | Projects are expected to adapt to all changes within their context that have the potential to significantly impact project success. | Project success depends to a large degree on the fit of the project strategy to its context. Therefore, if the context changes significantly, it is likely that the project needs to deviate from its original plan and adapt to these new conditions. If a project is found not to have adapted to significant changes to the degree necessary for continued success in the past, reasons for this should be explored. In addition, the identified shifts in context and their consequences for the project as well as options for adaptation need to be explained.
2.6. | How is the quality of the strategic / political steering structure to be judged? | 1) The strategic / political steering structure refers to structures, roles of individual stakeholders and procesess to reach relevant steering decisions related to the project. This includes meetings as well as other communication and decision-making formats. | 1) Identify all political actors with a strong and legitimate interest in the project (political partners identified in the project proposal, German funding ministry, any other relevant actors) via analysis of project documents and interviews with relevant sources. 2) Assess if meetings, communication and desicion-making formats are in place and frequntly used. 3) Assess the quality of this structure. A high quality steering structure comprises a) regular meetings and the use of communication and fesicion-making formats b) presence of all relevant actors c) meaningful exchange of ideas, needs, priorities, results and challenges d) sufficient documentation and dissemination of results e) appropriate follow-up to decisions made. | Projects are expected to have a strategic / political steering structure in place which meets all quality criteria mentioned. | Project success depends on political support. If a project does not have a strategic / political steering structure in place or this structure is found lacking, reasons for this should be explored and suggestions provided on how such a structure could be established for the remainder of the project duration.
2.7. | How is the quality of the operational steering structure among the project consortium to be judged? | 1) The operational steering structure refers to structures, roles of individual stakeholders and procesess to reach relevant steering decisions related to the project (meetings as well as other communication and decision-making formats). | 1) Identify all implementing partners via consultation of all project proposals. 2) Assess if meetings, communication and desicion-making formats are in place and frequntly used. 3) Assess the quality of this structure. A high quality steering structure comprises a) regular meetings and the use of communication and fesicion-making formats b) presence of all relevant actors c) meaningful exchange of ideas, needs, priorities, results and challenges d) sufficient documentation and dissemination of results e) appropriate follow-up to decisions made. | Projects are expected to have a operational steering structure in place which meets all quality criteria mentioned. | Project implementation often needs to be coordinated amongst a number of different implementing organisations. If a project does not have an operational steering structure in place or this structure is found lacking, reasons for this should be explored and suggestions provided on how such a structure could be established for the remainder of the project duration.

## Effectiveness
| Criterion | Guiding question
| Effectiveness | To what extent can the project be expected to achieve its objectives?
No. | Evaluation question | Relevant definitions | Baseline approach | Baseline assessment standards | Intent and opportunities for learning
3.1. | To what extent is the theory of change of the project plausible? | 1) Since the results framework included in the project proposal is usually not detailed enough to enable plausibility checks, a more detailed theory of change needs to be reconstructed during the inception phase of the evaluation (see annex 3 Guidelines on ToC Reconstruction for IKI MTEs). | 1) Reconstruct a theory of change for the project (see annex 3 Guidelines on ToC Reconstruction for IKI MTEs). 2) Identify three local experts (representatives of target groups, political partners, civil society, think tanks, universities etc.) with intricate knowledge of the topic and region the project is working on, including their overall political, economic and / or social context. 3) Provide these local experts with the reconstructed theory of change of the project (or a section of the theory relevant to them), including a verbal or written explanation of the underlying assumptions. 4) Once a common understanding of the intended results chains has been reached, gather feedback from the experts on the likelihood of success of each causal assumption from output to impact, including reasons for these assessments and suggestions on how to improve the project strategy. | The ToC is plausible if a) the intended changes are in the interest of the actors intended to change OR it is possible to implement planned prohibitions or constraints effectively b) the intended changes are in the interest of the political authorisers of the actors intended to change c) no significant barriers to the realisation of the indirect outcomes beyond the sphere of influence of the project are present. ToCs are plausible if they meet all of the criteria listed above. | While the functionality of a sample of project outputs is being examined in detail under the criterion of effectiveness, this question is meant to enable expert assessments of the likelihood of success of the overall project strategy, focussing on the (presumably large amount of) intended indirect outcomes within the context of the direct target groups (their place of work or residence, their partner organisations or clients, their community etc.) and beyond, as well as the intended impacts. Besides being logically consistent in themselves, good theories of change need to be grounded in local political, economic and social circumstances as much as possible to be useful tools for project planning, implementation and monitoring. Local actors are therefore best placed to assess their plausibility, especially if these actors are themselves part of the overall change envisioned by the project. If parts of the theory of change of the project are assessed to be implausible, suggestions should be provided on the changes necessary to increase realism and the likelihood of success.
3.2. | To what extent have the planned targets been achieved so far? | 1) Planned targets are those targets set in connection with the indicators provided in the project proposal. | 1) Enumerate all targets that should have been achieved at the time of the evaluation based on information provided in the most recent project documents. 2) Identify those targets that have actually been (partially or fully) achieved at the time of the evaluation based on the most recent project reporting. 3) Compare these lists and identify any targets that have not been achieved as planned. 4) Check targets that were achieved on time for plausibility. 5) If targets have not been achieved as planned, it should be determined if this was based on changes within the project context or due to other factors. | Overall, projects are expected to have achieved at least 80% of their targets as planned. | Changes in target achievement are a normal aspect of project implementation, especially if they are based on changes in the project context. At the same time, project duration is limited and the sequence of target achievement is often important to project success. Therefore, a backlog of more than 20% of target achievement should be flagged, changes to target achievement that occured due to project-internal reasons should be identified and suggestions provided on which targets should be prioritised and how they can be achieved as soon as possible.
3.3. | To what extent have the planned products and services intended for use by target groups been delivered so far? | 1) The products and services of the project intended for use by target groups are referred to as outputs (Please refer to annex 3 Guidelines on ToC reconstruction for IKI MTEs) 2) Planned products and services are those outputs that were meant to have been delivered to project-external target groups at the time of the evaluation according to the most recent version of the project proposal. | 1) Identify all outputs that have actually been delivered at the time of the evaluation based on the most recent project reporting and - if available, internal monitoring documents. 2) Compare these lists and identify any outputs that have not been delivered as planned. 3) If outputs have not been provided as planned, it should be determined if this was based on changes within the project context or due to other factors. | Overall, projects are expected to have delivered at least 80% of their outputs as planned. | Changes in output delivery are a normal aspect of project management, especially if they are based on changes in the project context. At the same time, project duration is limited and the sequence of output delivery is often important to project success. Therefore, a backlog of more than 20% of outputs should be flagged, changes to output delivery that occured due to project-internal reasons should be identified and suggestions provided on which outputs should be prioritised for delivery.
3.4. | To what extent were the needs of the intended target groups considered during the planning and delivery of individual project products and services? | 1) For analysis purposes, the products and services of the project for use by target groups are referred to as outputs 2) Needs of the intended target groups include any specific knowledge, skills, opportunities, resources etc. that are currently lacking but necessary to realise the intended outcomes, as well as general circumstances that need to be considered when delivering products and services (e.g. language skills, prefered formats of delivery, expenditure of time, opportunity costs etc.). 3) An output cluster is a coherent group of project products and services complimentarily designed to support a specific intended outcome within one (broadly defined) target group. They may or may not correspond to a work package described in the project proposal Please refer to annex 3 Guidelines on ToC reconstruction for IKI MTEs regarding aspect 1, 2 and 3 | 1) Due to budget and time constraints, this analysis will have to be limited to a sample of all project outputs delivered so far. Therefore, based on the reconstructed theory of change of the project, select up to two output clusters. Preferably choose clusters in which enough outputs have already been delivered to enable relevant analysis. Chosen clusters should be important to the functioning of the project as a whole. 2) Reconstruct detailed nested theories of change for these clusters, covering the content and format of each individual output, their intended target groups, their intended direct outcomes within these target groups as well as their intended indirect outcomes within the direct environments of the target groups (i.e. their everyday life, their job, their organisation, their community etc.) (see annex 3 Guidelines on ToC Reconstruction for IKI MTEs). These theories of change should also make clear how the individual outputs are aligned with each other and interact to support the realisation of the intended overall outcome. 3) For each individual output within the cluster(s) that has already been delivered, analyse the planning process and assess a) how and to what extent the project identified the specific and concrete needs, opportunities and / or challenges of the intended target groups in advance and b) how and to what extent the project incorporated these specific needs, opprtunities and / or challenges in the design of the individual outputs. | Projects are expected to base the design and delivery of all their products or services on the needs and circumstances of the intended target groups. To avoid biases and misconceptions as much as possible, knowledge about these needs and circumstances should not be merely generally assumed, but derived from meaningful direct consultations with these target groups (or knowledgable local experts) well in advance of output delivery. In lieu of direct consultations with the target groups themselves, input from knowledgeable and experienced local experts would be acceptable as well. These needs and circumstances need to be meaningfully incorporated into the design and delivery of the project outputs to the extent possible. | Most of the time, project success depends on contextual developments to a large degree. Only the timely delivery of high-quality products to relevant target groups in a manner maximising the likelihood of achieving the intended direct effects is firmly within the sphere of influence of the project. This question is intended to assess if the project is using its limited influence to maximum effect. Therefore, the evaluation should entail a detailed analysis of the planning and delivery of a significant number of individual outputs in order to assess the degree to which they are tailored to the specific needs and circumstances of their intended target groups. If the project is found not to have considered the needs of the intended target groups during planning and delivery of project outputs, reasons for this should be explored and suggestions made on how this could be improved in the future.
3.5. | To what extent are the products and services of the project having their intended direct effects? | 1) For analysis purposes, the products and services of the project for use by target groups are referred to as outputs 2) Here, intended direct effects denote all causal elements necessary from output delivery to the achievement of the intended direct outcomes within the direct target groups, i.e. output reach, user satisfaction, output use and degree of realisation of intended direct outcomes. These are often not made explicit in project documents 3) An output cluster is a coherent group of project products and services complimentarily designed to support a specific intended outcome within one (broadly defined) target group. They may or may not correspond to a work package described in the project proposal. Please refer to annex 3 Guidelines on ToC reconstruction for IKI MTEs regarding aspect 1, 2 and 3 | 1) As with question 3.4., analysis of this question will need to be limited to a sample of project outputs delivered so far. Therefore, the output clusters selected to answer question 3.4. should be analysed further here. 2) Based on the nested theories of change prepared to analyse question 3.4., analyse the following questions by gathering feedback from representatives of the target groups / users of all outputs of the cluster(s) that have already been delivered: a) to what extent have the inteded target groups been reached? b) to what extent where target groups satisfied with the quality of the output? c) to what extent do the intended target groups use the outputs? d) to what extent did the output contribute to the intended direct outcome (new knowledge, attitudes, motivations, opportunities, constraints etc.) within the target groups? | Overall, an 80% success rate is expected for all outputs, i.e. 80% of output users are representatives of intended target groups, 80% of output users report satisfaction with the quality of the output, 80% of people reached are using the output, and 80% of output users report that the intended changes in knowledge, attitudes etc. have been achieved. | Most of the time, project success depends on contextual developments to a large degree. Only the timely delivery of high-quality products to relevant target groups in a manner maximising the likelihood of achieving the intended direct effects is firmly within the sphere of influence of the project. This question is intended to assess if the project is using its limited influence to maximum effect. Therefore, the evaluation should entail a detailed analysis of the initial steps of a number of causal pathways based on a sample of products and services provided by the project in detail. If the project is found not to have achieved the expected results regarding the different aspects of output success, reasons for this should be explored and suggestions made on how output delivery and use could be improved in the future.
3.6. | To what extent are products and services of the project having an effect beyond their direct target group? | 1) For analysis purposes, the products and services of the project for use by target groups are referred to as outputs 2) Here, effects beyond the direct target group denotes intended indirect outcomes, i.e. changed behaviour by the output users, which is in turn assumed to affect changes within the immediate context of the target groups reached (i.e. their organisation, peer group, community, physical surroundings etc.). Please refer to annex 3 Guidelines on ToC reconstruction for IKI MTEs regarding aspect 1 and 2 | 1) The sample for this analysis consists of those outputs analysed under question 3.5. that were shown to have achieved their intended direct outcome (i.e. new knowledge, attitudes, motivations, opportunities, constraints etc. of output users) to a significant degree. 2) Additional questions to be analysed by gathering feedback from the change agents / indirect target groups themselves, i.e. those individuals or organisations intended to change their behaviour and / or initiate change within their own context, organisation, community etc., are: a) to what extent did the use of project outputs lead to behavioural changes within the target groups? b) To what extent did these behavioural changes lead to intended changes within the immediate context of the target groups reached? c) which are the main factors (if any) impeding the realisation of indirect outcomes? | Overall, a 60% success rate is expected for all intermediate outcomes, i.e. 60% of output users have changed their behaviour as intended and in 60% of cases intended changes within the immediate context of the target groups are observable. | This question provides an opportunity to take the analysis regarding questions 3.5. one step further. Here, the focus is on intermediary effects, even though their realisation is outside the sphere of influence of the project. Even though this is the case, information on the degree of realisation of intermediary outcomes is crucial for overall project success and should lead to changes in the project approach. If intermediary outcomes have not been realised as expected, reasons for this should be explored and suggestions made on which additional products or services should be provided by the project to increase the likelihood of achievement of the outcomes in question.
3.7. | This question is only relevant for projects selected for financing from 2023 onwards that have prepared a Project Gender Action Plan (P-GAP). To what extent have the planned products or services intended to support gender equality been delivered so far? | 1) For analysis purposes, the products and services of the project intended for use by target groups are referred to as outputs 2) Planned products and services are those outputs that were meant to have been delivered to project-external target groups at the time of the evaluation according to the most recent version of the project proposal. 3)The Project Gender Action Plan (P-GAP), which must be submitted during the preparation phase, should include a list of specific products and services designed to promote gender equality and / or products or services mainly intended for other purposes which include aspects that support gender equality. Please refer to annex 3 Guidelines on ToC reconstruction for IKI MTEs regarding aspect 1 and 2 | 1) Enumerate all gender-related outputs that should have been delivered at the time of the evaluation based on information provided in the Project Gender Action Plan. 2) Identify all gender-related outputs that have actually been delivered at the time of the evaluation based on the most recent project reporting. 3) Compare these lists and identify any outputs that have not been delivered as planned. 4) If outputs have not been provided as planned, it should be determined if this was based on changes within the project context or due to other factors. | Overall, projects are expected to have delivered at least 80% of their gender-related outputs as planned. | IKI is striving for gender justice. As part of this effort, relevant projects should deliver products and services specifically designed to support gender equality in their strategy. Changes in output delivery are a normal aspect of project management, especially if they are based on changes in the project context. At the same time, project duration is limited and the sequence of output delivery is often important to project success. Therefore, a backlog of more than 20% of outputs should be flagged, changes to output delivery that occured due to project-internal reasons should be identified and suggestions provided on which outputs should be prioritised for delivery.
3.8. | This question is only relevant for projects selected for financing from 2023 onwards that have prepared a Project Gender Action Plan (P-GAP). To what extent are the products and services of the project intended to support gender equality having their intended direct effects and to what extent are they having an effect beyond their direct target group? | 1) For analysis purposes, the products and services of the project intended for use by target groups are referred to as outputs 2) Here, intended direct effects denote all causal elements necessary from output delivery to the achievement of the intended direct outcomes within the direct target groups, i.e. output reach, user satisfaction, output use and degree of realisation of intended direct outcomes. These are often not made explicit in project documents 3) Here, effects beyond the direct target group denotes intended indirect outcomes, i.e. changed behaviour by the output users, which is in turn assumed to affect changes within the immediate context of the target groups reached (i.e. their organisation, peer group, community, physical surroundings etc.) 4)The Project Gender Action Plan (P-GAP), which must be submitted during the preparation phase, should include a list of specific products and services designed to promote gender equality and / or products or services mainly intended for other purposes which include aspects that support gender equality. Please refer to annex 3 Guidelines on ToC reconstruction for IKI MTEs regarding aspect 1, 2 and 3 | 1) Draw a sample of two individual gender-related outputs that have been delivered recently and are part of different work packages, intended for different target groups and delivered by different consortium members. 2) Reconstruct detailed theories of change for these individual outputs, covering their target groups as well as the intended direct and indirect outcomes for each (Please refer to annex 3 Guidelines on ToC Reconstruction for IKI MTEs). 3) Regarding direct outcomes, analyse the following questions by gathering feedback from representatives of the target groups / users of outputs themselves: a) to what extent have the inteded target groups been reached? b) to what extent where target groups satisfied with the quality of the output? c) to what extent do the intended target groups use the outputs? d) to what extent did the output contribute to the intended direct outcome (new knowledge, attitudes, motivations, opportunities, constraints etc.) within the target groups, especially regarding any gender-related changes? 4) Regarding indirect outcomes, analyse the following: a) to what extent did the use of project outputs lead to behavioural changes within the target groups? b) To what extent did these behavioural changes lead to intended changes within the immediate context of the target groups reached? c) which are the main factors (if any) impeding the realisation of intermediate outcomes? | Regarding direct outcomes, an 80% success rate is expected for all outputs, i.e. 80% of output users are representatives of intended target groups, 80% of output users report satisfaction with the quality of the output, 80% of people reached are using the output, and 80% of output users report that the intended changes in knowledge, attitudes etc. have been achieved. Regarding indirect outcomes, a 60% success rate is expected, i.e. 60% of output users have changed their behaviour as intended and in 60% of cases intended changes within the immediate context of the target groups are observable. | IKI is striving for gender justice. As part of this effort, relevant projects should deliver products and services specifically designed to support gender equality in their strategy. Most of the time, project success depends on contextual developments to a large degree. Only the timely delivery of high-quality products to relevant target groups in a manner maximising the likelihood of achieving the intended direct effects is firmly within the sphere of influence of the project. This question is intended to assess if the project is using its limited influence to maximum effect. Therefore, the evaluation should entail a detailed analysis of the initial steps of a number of causal pathways based on a sample of products and services provided by the project in detail. If the project is found not to have achieved the expected results regarding the different aspects of output success, reasons for this should be explored and suggestions made on how output delivery and use could be improved in the future.
3.9. | This question is only relevant for projects that reportedly contribute to at least one of the four IKI Strategic Objectives provided that ZUG identified potential needs for adjustments that would strengthen the likelihood of the project contributing to the stategic objectives as intended. Information on whether the question applies for a given project will be included in the respective tender documents. Which specific adjustment to the project's delivery of its outputs would most enhance its contributions to relevant IKI Strategic Objectives? | 1) Adjustments to the project's delivery of its outputs refers to any adaptations in the delivery of intended outputs (i.e. additional efforts encouraging the uptake of the outputs by target groups, intensification or prioritisation of certain intended steps of output delivery, slight changes to priority setting within an output objective). 2) IKI Strategic Objectives refer to the four strategic objectives (i.e. Raising ambitions, Improving the enabling environment, Implementation, Mobilising private finance) as defined in the IKI Strategy. | 1) Plan for a 1-2h exchange with ZUG and the team lead to clarify scope and focus of the question (i.e. which Strategic Objectives are of particular interest and why, which outputs of the project are most relevant). ZUG will brief the team lead on any relevant provisions related to the Strategic Objectives needed for the investigation. All provisions on monitoring and reporting can be found in the IKI Project Planning and Monitoring Guidelines. 2) Ensure that identified outputs are adequately considered when reconstructing the theory of change and collecting data for answering the other evaluation questions. 3) After data collection and in the synthesis phase plan for 1-2h exchange with ZUG and the team lead to jointly discuss findings and identify potential recommendations on which aspects in the delivery of outputs the project should be strengthened or intensified to increase the likelihood that the project contributes to the Strategic Objective in question.

## Sustainability
| Criterion | Guiding question
| Sustainability | What measures has the project planned to support the continuation of the project's positive achievements after the IKI funding has ended?
No. | Evaluation question | Relevant definitions | Baseline approach | Baseline assessment standards | Intent and opportunities for learning
4.1. | To what extent did the project develop an exit strategy to support the sustainability of the project results after the implementation phase has ended? | 1) An exit strategy is a document describing in detail how the project plans to ensure the sustainability of its results after the project itself has ended. | 1) Clarify if the project has prepared a dedicated exit strategy. If this is not the case, it might be possible to derive plans for the exit process from a range of other documents. 2) Assess the quality of the exit strategy against relevant standards. | A good exit strategy should a) be developed in close collaboration with the main local implementing partners b) include an analysis of which activities will need to be implemented or maintained after end of project c) identify local partners willing to take over these activities d) identify the resources needed by the respective partner to be able to maintain the activities e) identify ways in which these resources will be made available to the respective partner. It is expected that exit strategies meet all of these expectations. | IKI projects are expected to support lasting change. To ensure sustainability of results, work often needs to continue even after the project has ended, usually with local actors, using local resources, in the lead. To support a smooth transition, an exit strategy is necessary. If no such strategy exists or the existing strategy does not meet relevant quality standards, reasons for this should be explored a suggestions provided on how a useful and realistic exit strategy could be developed during the remainder of the project.

## Safeguards
| Criterion | Guiding question
| Safeguards | To what extent is the project effectively reflecting, avoiding, minimising and/or mitigating negative environmental and social risks and impacts?
No. | Evaluation question | Relevant definitions | Baseline approach | Baseline assessment standards | Intent and opportunities for learning
5.1. | Are the planned safeguards measures being implemented? | 1) Planned safeguards measures are listed in the safeguards section of the project proposal. | 1) Enumerate all safeguards measures that should have been delivered at the time of the evaluation based on information provided in the most recent project documents. 2) Identifiy all safeguards measures that have actually been delivered at the time of the evaluation based on the most recent project reporting. 3) Compare these lists and identify any measures that have not been delivered as planned. 4) If safeguards measures have not been provided as planned, it should be determined if this was based on changes within the project context or due to other factors. | Overall, projects are expected to have delivered at least 80% of their safeguards measures as planned. | IKI is committed to complying with environmental and social standards to enhance the effectiveness, sustainability and quality of projects. To this end, projects carrying risks in this regard are obliged to implement specific measures aimed at helping to avoid / prevent, minimise / reduce, mitigate or remedy adverse impacts of project activities. Changes in the delivery of measures are a normal aspect of project management, especially if they are based on changes in the project context. At the same time, project duration is limited and the timing of delivery of safeguards measures is often important. Most importantly, safeguards measures need to be implemented at the same time as risky project activities are implemented in order to be able to prevent or mitigate negative impacts.Therefore, a backlog of more than 20% of safeguards measures should be flagged, changes to the delivery of safeguards measures that occured due to project-internal reasons should be identified and suggestions provided on which safeguards measures should be prioritised for delivery.
5.2. | Are the safeguards measures deemed adequate to avoid, minimise or mitigate negative impacts? | 1) Projects aim to prevent, minimise, mitigate or remedy adverse impacts and, ideally, to maximise positive impacts on the environment and people | 1) Identify representatives of project-affected groups or communities whose livelihood and / or well-being was supposed to be safeguarded by measures implemented by the project so far. In case of safeguards measures related to the protection of ecosystems, representatives of organisations or communities tasked with their protection should be identified. 2) Collect feedback from these groups on the effectiveness of the implemented measures. Also include assessments by other (project) stakeholders on these issues. | Overall, we expect all safeguards measures to be effective, i.e. affected populations report that the measure effectively avoided / prevented, minimised / reduced, mitigated or remedied adverse impacts of project activities. | Affected groups or communities are best placed to assess if safeguards measures have been effective. Therefore, every effort should be made to receive valid feedback from them directly. If measures are found not to have had the intended effect, reasons for this should be explored and suggestions provided on additional measures to remedy the situation.
5.3. | Do you have any indication that project activities have had a negative impact on people or the environment so far? | 1) Projects aim to prevent, minimise, mitigate or remedy adverse impacts and, ideally, to maximise positive impacts on the environment and people | 1) Include questions regarding the potential occurance of negative effects of project activities in all data collection from project-external sources. Particular attention should be paid to assessments by representatives of project-affected groups or communities. If there are indications of negative impacts, please point out which of the IFC Performance Standards are affected. | Projects are expected not to cause any significant negative effects on people and ecosystems in the implementing area and make an appropriate effort to remedy negative consequences when they do occur and prevent any further negative impacts. | Projects are expected to manage risks associated with their activities pro-actively. Therefore, negative effects are expected to be few and of low intensity. If this is not the case, reasons for this should be explored and suggestions provided on how negative effects that have already realised can be remedied as well as on how their likelihood can be minimised in the future.
5.4. | This question only needs to be answered for projects that have agreed to adhere to the IKI Independent Complaint Mechanism Policy. To what extent does the project provide information on the IKI Independent Complaint Mechanism (ICM) to the general public? | 1) The Independent Complaint Mechanism is an institutionalised accountability mechanism intended to enable people who suffer (potential) negative social and / or environmental consequences from IKI projects, or who wish to report the improper use of funds, to voice their complaints and seek redress. | 1) Check the project website for information on the ICM. 2) Based on a random sample of past events, assess to what degree and how the project creates awareness about the ICM at events. 3) Include questions regarding awareness of the ICM as well as on how the project might be able to improve its approach in all data collection from project-external sources. | Projects that have agreed to adhere to the ICM Policy are expected to create awareness for the ICM by providing relevant information, including on how to submit complaints, online and at events. The information should be easy to find (i.e. prominently placed) and easy to understand (i.e. provided in the local language(s) using simple terms). | To ensure sustainability and compliance with national and international standards, organisations implementing IKI projects are responsible for compliance with social and environmental standards and for the lawful use of approved funding. The independent complaint mechanism is intended to bolster these principles in the long term. However, the mechanism can only be effective if the general public is aware of its existence and knows how to file complaints. If the findings suggest that opportunities to create awareness of the ICM have not been utilised fully, reasons for this should be explored and suggestions provided on how this can be improved in the future.